## Action Items
CAD Manager's Priorizing Spreadsheet | Task Type | Project Due Date | Work Hours Required | Start Date (Calculated) | Date Alert | Contact Person | Examples Provided? | Notes
by Robert Green (rgreen@cad-manager.com) | Billable | 2022-02-20 | 80 | 2022-02-07 |  | Robert Green | Yes | P&ID creation CAD
| Billable | 2022-02-20 | 24 | 2022-02-02 |  | Robert Green | No | Electrical layout CAD
1. Input task type, due date and work hours required | Billable | 2022-02-20 | 40 | 2022-01-26 |  | Robert Green | No | Electrical submittal set
2. Task type is list driven for consistency | Development | 2022-02-20 | 24 | 2022-01-21 | ! In the past ! | Robert Green | No | P&ID plot routines
3. Start date will be computed for you based on a | Development | 2022-02-20 | 16 | 2022-01-19 | ! In the past ! | Robert Green | No | P&ID standards update
5 day work week. Note: Cell is locked. | Overhead | 2022-03-15 | 20 | 2022-03-10 |  | Robert Green | Pending | Refresh title blocks
4. Print range set from D1 to J23 landscape | Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
| Billable | 2022-12-30 | 0 | 2022-12-30
Formulas:
Start Date (Calculated) = WORKDAY([Project Due Date],-([Work Hours Required]/8),5)
Start Date (Calculated) = WORKDAY([Start Date (Calculated), row above],-([Work Hours Required]/8),5)
Date Alert = IF([Start Date (Calculated)]<TODAY(),"! In the past !","")